## Sheet1
Nr.	Date	Task	Deadline/Milestone
1	10.17.2018	Select Topic	Send Email with Topic
2	10.24.2018	Narrow down Topic, create Git
3	10.31.2018	Gather information about Chatbots
4	11.7.2018	Create Recipe Database
5	11.14.2018	Initialise Project with Telegram
6	11.21.2018	Basic Talk
7	11.28.2018	Provisional version with basic features
8	12.5.2018	Learn recipe feature
9	12.12.2018	Finish Software/Start writing
10	12.19.2018
11	01/08/2019		Paper Draft
12	01/15/2019		Reviews
13	1.23.2019	Incorporate changes into paper
14	01/29/2019		Final Submission